## Statistic
Test Report
Sprint |  |  |  | Total Test Case | Total Remain Bug | Note
Plan
Function/Screen |  | Estimate Date | Person In Charge | Note
Order Information |  |  | ManhPK | fix screen of LinhNK
Settings List |  |  | DungNV
Setting Details |  |  | DungNV
LOC
Member | Total Function/Screen | Total LOC
HieuNH | 13 | 1080
HoangLV | 9 | 960
DungNV | 8 | 840
ManhPK | 10 | 900

## Product Backlog with RTM
II
THE APPLICATION DEVELOPMENT PROJECT TOPIC (SWP391)
ASSIGNMENT FUNCTION DETAILS - ONLINE SHOPPING SYSTEM
Project: Online Shop |  |  | Total LOC: | 3840 | Group: 02 | [9 empty] | Group: 02
Project Backlog | [5 empty] | Final Developmennt Status | [5 empty] | Requirement Traceability Metrix
# | Function/Screen | Feature | Level | LOC | Original Function/Screen Details | Channge Request | Reason for CR | Planned iteration | Actual iteration | Person In Charge | Final status | Use Case ID | SDS | Source Code | Function Need to Verify | Verify Result | Tester | Demo video Link
2 | Home Page | Public | Medium | 120 | Show sliders, hot posts, featured products + the sider with the latest posts, static contacts/links - Shown slider information includes its image and title; the user is redirected to the slider's backlink on his/her clicking - Shown post information includes its thumbnail, title, brief-info; the user is redirected to the post's details on his/her clicking - Shown product information includes its thumbnail, title, brief information; the user is redirected to the product's details on his/her clicking |  |  | Iter1 | Iter1 | Nguyen Huu Hieu | Done | II. 2.4 UC-4_Home Page | III. 1.2 c. Home Page | - home.jsp - HomeController.java - Category.java - Products.java - Sliders.java - Blogs.java - BlogImage.java - DAO.java | F1: Show sliders, hot posts, featured products + the sider with the latest posts, static contacts/links F2: Shown slider information includes its image and title; the user is redirected to the slider's backlink on his/her clicking F3: Shown post information includes its thumbnail, title, brief-info; the user is redirected to the post's details on his/her clicking F4: Shown product information includes its thumbnail, title, brief information; the user is redirected to the product's details on his/her clicking | F1: Làm đúng yêu cầu. F2:Làm đúng yêu cầu. F3:Làm đúng yêu cầu. F4:Làm đúng yêu cầu. | HieuNH | https://youtu.be/MoxIkOk4X68
3 | Blogs List | Public | Simple | 60 | Show the posts paginatedly (sorted by updated date, paginated) + the sider with the post search box, post categories, the latest posts, and static contacts/links; Shown post information includes its thumbnail, title, brief-info; the user is redirected to the post's details on his/her clicking |  |  | Iter1 | Iter1 | Phung Kim Manh | Done | II. 2.8 UC-8_Blog List | III. 1.2 g. Blog List | - bloglist.jsp - BlogControl.java - BlogDAO.java - Blog.java | F1: Show the posts paginatedly (sorted by updated date, paginated) F2: + the sider with the post search box, post categories, the latest posts, and static contacts/links; F3: Shown post information includes its thumbnail, title, brief-info; the user is redirected to the post's details on his/her clicking | F1: Làm đúng yêu cầu. F2:Làm thiếuyêu cầu. F3:Làm đúng yêu cầu. | ManhPK | https://youtu.be/eWIHLeEuOyA https://youtu.be/w3UFla-M0-g
4 | Blog Details | Public | Simple | 60 | Show post details (including title, author, updated date, category, and post details) + the sider with the post search box, post categories, static contacts/links |  |  | Iter1 | Iter1 | Phung Kim Manh | Done | II. 2.9 UC-9_Blog Dtail | III. 1.2 h. Blog Detail | -blogdetail.jsp -Blogdetai.java -BlogDAO.java -Blog.java | F1: Show post details (including title, author, updated date, category, and post details) F2: + the sider with the post search box, post categories, static contacts/links | F1: Làm đúng yêu cầu. F2:Làm thiếuyêu cầu. | ManhPK | https://youtu.be/ZcWrAQnH3KE https://youtu.be/87EehL1FV7E
5 | Products List | Public | Medium | 120 | Show the products paginatedly (sorted by updated date) + the sider with the product search box, product categories, the latest products, and static contacts/links; - Shown product information includes its thumbnail, title, brief information, original price, and sale price; - The user is redirected to the product's details on his/her clicking on the product - The user can choose to add the product to the cart or to feedback on the product by clicking the product's Buy & Feedback buttons responsively |  |  | Iter1 | Iter1 | DungNV | done | II. 2.5 UC-5_Product List | III. 1.2 i. Product List | - productList.jsp - ProductListController.java - ProductListUpdateController.java - ProductListDAO.java - Category.java - Products.java | F1: Show the products paginatedly (sorted by updated date) F2: + the sider with the product search box, product categories, the latest products, and static contacts/links; F3: - Shown product information includes its thumbnail, title, brief information, original price, and sale price; F4: - The user is redirected to the product's details on his/her clicking on the product F5: - The user can choose to add the product to the cart or to feedback on the product by clicking the product's Buy & Feedback buttons responsively This should be Medium function | F1: pass F2: pass F3: pass F4: pass F5: pass | dungnv | https://www.youtube.com/watch?v=P50KJEUSp40&ab_channel=Noone
6 | Product Details | Public | Medium | 120 | Show product details (including title, category, images, original price, sale price, and product details) + the sider with the product search box, product categories, the latest products, and static contacts/links |  |  | Iter 1 | Iter 1 | Phung Kim Manh | Done | II. 2.12 UC-12_Product Details | III. 1.2. k. Product Details | productDetails.jsp ProductDetailController.java DAO.java Category.java Products.java | F1: Show product details (including title, category, images, original price, sale price, and product details) F2: + the sider with the product search box, product categories, the latest products, and static contacts/links | F1: Làm đúng yêu cầu. F2: Làm đúng yêu cầu. | Phùng KIm Mạnh | https://youtu.be/5krEdXLuSZg
7 | Cart Details | Public | Medium | 120 | Show the cart details with list of the user's chosen products (including Id, title, price, quantity, total cost) and the total order price + the sider with the product search box, product categories, the latest products, and static contacts/links; The user can - Change the quantity of each product: the total cost is automatically adjusted - Choose to delete/remove product by clicking on the deleting icon - Click the Choose More Product button to go to Products List page - Click the Check Out button to go to the Cart Contact page Please notes: the user's chosen products from the last browsing session are remained in his/her cart until s/he submit the cart. However, the product prices are updated with the latest prices in the system |  |  | Iter2 | Iter2 | Le Viet Hoang | Done | II. 2.19 UC-19_Cart Details | III. 1.2.17. Cart Details | CartDetail.jsp CartDetailController.java DAO.java OrderDAO.java Item.java AddCartController.java | F1: Show the cart details with list of the user's chosen products (including Id, title, price, quantity, total cost) and the total order price F2: + the sider with the product search box, product categories, the latest products, and static contacts/links; The user can F3: - Change the quantity of each product: the total cost is automatically adjusted F4: - Choose to delete/remove product by clicking on the deleting icon F5: - Click the Choose More Product button to go to Products List page F6: - Click the Check Out button to go to the Cart Contact page F7: Please notes: the user's chosen products from the last browsing session are remained in his/her cart until s/he submit the cart. F8:However, the product prices are updated with the latest prices in the system | F1: Pass F2: Pass F3: Pass F4: Pass F5: Pass F6: Pass F7: Pass F8: Pass | Le Viet Hoang | https://youtu.be/4XJFfoYIg_0
8 | Cart Contact | Public | Medium | 120 | Show the list of user chosen product (including id, title, price, quantity, total cost), the total order price and the receiver information (including full-name, gender, email, mobile, address, notes) for user to edit/input + the sider with the product search box, product categories, the latest products, and static contacts/links - In case the user has logged in, the receiver information would be filled with the user's information - The user can click the Change button to come back to the Cart Details page for changing the choosing products, click the Submit button to submit the order before redirecting user to the Card Completion or Error page (due to technical error or any out-of-stock product) |  |  | Iter2 | Iter2 | Le Viet Hoang | Done | II. 2.20 UC-20_Cart Contact | III. 1.2.18. Cart Contact | CartContact.jsp CartContactController.java DAO.java OrderDAO.java Item.java ModifyAddressController.java Product.java | F1: Show the list of user chosen product (including id, title, price, quantity, total cost), the total order price and the receiver information (including full-name, gender, email, mobile, address, notes) for user to edit/input F2: + the sider with the product search box, product categories, the latest products, and static contacts/links F3: - In case the user has logged in, the receiver information would be filled with the user's information F4: - The user can click the Change button to come back to the Cart Details page for changing the choosing products, F5: click the Submit button to submit the order before redirecting user to the Card Completion F6: or Error page (due to technical error or any out-of-stock product) | F1: Pass F2: Pass F3: Pass F4: Pass F5: Pass F6: Pass | Le Viet Hoang | https://youtu.be/ZlyVbREU7TM
9 | Cart Completion | Public | Complex | 240 | This page show the cart completion notes + the sider with the product search box, product categories, the latest products, and static contacts/links; Before this page is shown: - The Order status is changed to submitted; - The product's available quantities are updated accordingly - The submitted order is assigned automatically to the active salers rotatedly - If the receiver information (name, email, mobile, gender) is new or changed (checking via the email0, the latest receiver information is stored in the system as latest & historical system contact information (for the marketing's reference later) -OK - The customer/user would be received the order confirmation & payment guides via his/her email. Those information is shown on the page also. The payment information (banking account,...) are taken from the system configuration file |  |  | Iter2 | Iter2 | DungNV | Done | II. 2.1 UC-15_Cart Completion | III/1.2/ 22. Cart Completion | cartCompletion.jsp CartCompletionController.java CartCompletionDAO.java | F1: This page show the cart completion notes F2: + the sider with the product search box, product categories, the latest products, and static contacts/links; Before this page is shown: F3:- The Order status is changed to submitted; F4: - The product's available quantities are updated accordingly F5: - The submitted order is assigned automatically to the active salers rotatedly F6: - If the receiver information (name, email, mobile, gender) is new or changed (checking via the email0, the latest receiver information is stored in the system as latest & historical system contact information (for the marketing's reference later) F7: - The customer/user would be received the order confirmation & payment guides via his/her email. F8: Those information is shown on the page also. F9: The payment information (banking account,...) are taken from the system configuration file | F1: Pass F2: Pass F3: Pass F4: Pass F5: Pass F6: Pass F7: Pass F8: Pass F9: Pass |  | https://www.youtube.com/watch?v=a5af48aLmO4
10 | Feedback | Public | Simple | 60 | On receiving the bought products successfully, the receiver would receive a confirmation email with the guides to feedback on each of the received product; Beside, the user/receive could also give the feedback (on a specific product or general feedback) via the website; The user also call this screen from the system menu on the header; The feedback information includes contact information (full name, gender, email, mobile), rated star, the attached images and the contact's free-format feedback The page sider is also shown with the product search box, product categories, static contacts/links; |  |  | Iter3 | Iter3 | Nguyen Huu Hieu | Done | II. 2.35 UC-35_Feedback | III 1.2 28. Feedback | cus-feedback.jsp FeedbackController.java DAO.java | F1: On receiving the bought products successfully, the receiver would receive a confirmation email with the guides to feedback on each of the received product; F2: Beside, the user/receive could also give the feedback (on a specific product or general feedback) via the website; F3: The user also call this screen from the system menu on the header; F4: The feedback information includes contact information (full name, gender, email, mobile), rated star, the attached images and the contact's free-format feedback F5: The page sider is also shown with the product search box, product categories, static contacts/links; | F1: done F2:done F3:done F4:done F5:done | HieuNH | https://youtu.be/_xkOcEUr4R4
11 | Order List | Warehouser | Medium | 120 | Show the list of orders paginatedly - The list can be shorted by status - Allow the users to filter the order by the status - Allow the user to search the orders by order id,full_name - On choosen status can update new status order |  |  | Iter3 | Iter3 | Nguyen Huu Hieu | Done | II. 2.34 UC-34_Order List (Warehouser) | III 1.2 37. Order List (Warehouser) | WarehouserOrderList.java OrderDAO.java order-list.jsp | F1: 'Show the list of orders paginatedly F2: - The list can be shorted by status F3: - Allow the users to filter the order by the status F4: - Allow the user to search the orders by order id, customer name F5: - On choosen status can update new status order | F1: done F2:done F3:done F4:done F5:done | HieuNH | https://youtu.be/qzsqB21iBj0
12 | User Login | Common | Simple | 60 | This is a pop-up screen which allows the user to enter email & password to login; on this page, there are also options for user to register new information or reset the password for the case s/he forget it |  |  | Iter1 | Iter1 | Nguyen Huu Hieu | Done | II. 2.1 UC-1_Login System | III. 1.2 a UC-2_Login System | login.jsp LoginController.java. Customers.java Employees.java loginEmployee.jsp EmployeeDAO.java CustomerDAO.java | F1: 'This is a pop-up screen which allows the user to enter email & password to login; on this page, F2: there are also options for user to register new information or reset the password for the case s/he forget it | F1: Làm đúng yêu cầu. F2: Làm đúng yêu cầu. | Nguyen Huu Hieu | https://youtu.be/AC-EfQyJzJY
13 | Remeber Account | Common | Simple |  | Remember email and password |  |  | Iter1 | Iter1 | Nguyen Huu Hieu | Done | II. 2.2 UC-2_Remember Me | III. 1.2 a UC-2_Login System | login.jsp LoginController.java. | F1: If click to checkbox "Remember Me" will be remember email and password 7 days. F2: If not click to checkbox "Remember Me" not remember email and password | F1: Làm đúng yêu cầu. F2: Làm đúng yêu cầu. | Nguyen Huu Hieu | https://youtu.be/wIZqYtAZfhE
14 | User Logout | Common | Simple |  | This use case allows users can logout the system |  |  | Iter1 | Iter1 | Nguyen Huu Hieu | Done | II. 2.3 UC-3_Logout | III. 1.2 c. Home Page | LogoutController.java home.jsp | F1: Click to logout redirect to Home Page | F1: Làm đúng yêu cầu. | Nguyen Huu Hieu | https://youtu.be/a_f0HxgZXvA
15 | User Register | Common | Simple | 60 | This is a pop-up screen which allows the user to register himself/herself to the system by inputing following information: full name, gender, email, mobile, and address; User then need to verify by clicking the link sent via email to him/her before being able to access the system |  |  | Iter1 | Iter1 | Nguyen Khang Linh | Done | II. 2.11 UC-11_User Register | III. 1.2 b. User Register | register.jsp RegisterController.java | F1: 'This is a pop-up screen which allows the user to register himself/herself to the system by inputing following information: full name, gender, email, mobile, and address; F2: User then need to verify by clicking the link sent via email to him/her before being able to access the system | F1: Làm đúng yêu cầu. F2: Chưa đúng yêu cầu. Thiêu link reset password - đã fixed | Nguyen Khang Linh | https://youtu.be/GUKcjFTFJ5A
16 | Reset Password | Common | Medium | 120 | The user to input his/her email to receive the reset password link. This link is sent to the user's email for his/her password resetting. - On clicking the link, the user is redirected to the password resetting page in which s/he input new password (twice) for the system access - Note that the link is only available for a specific time duration as configured in the system config file. |  |  | Iter1 | Iter1 | Le Viet Hoang | Done | II. 2.6 UC-6_Reset Password | III. 1.2 e Reset Password | ForgotPassword.jsp ForgotPasswordController.java EnterOtp.jsp OtpController.java NewPassword.jsp NewPasswordController.java | F1: 'The user to input his/her email to receive the reset password link. This link is sent to the user's email for his/her password resetting. F2: - On clicking the link, the user is redirected to the password resetting page in which s/he input new password (twice) for the system access F3: - Note that the link is only available for a specific time duration as configured in the system config file. | F1: Làm đúng yêu cầu. F2: Làm đúng yêu cầu. F3: Làm đúng yêu cầu | Le Viet Hoang | https://youtu.be/Y3n23IJg3Go
17 | Change Password | Common | Simple | 60 | This is a pop-up screen which allows the user to change his/her password by inputting his current password as well as new password (twice) |  |  | Iter1 | Iter1 | Le Viet Hoang | Done | II. 2.5 UC-5_Change Password | III. 1.2 d Change Password | ChangePassword.jsp ChangePasswordController.java | F1: 'This is a pop-up screen which allows the user to change his/her password by inputting his current password as well as new password (twice) | F1: Làm đúng yêu cầu. | Le Viet Hoang | https://youtu.be/Y3n23IJg3Go
18 | User Profile | Common | Simple | 60 | This is a pop-up screen which allows the user to edit his/her profile information, including the registered ones & the avatar image. Please note that s/he is not allowed to change the email |  |  | Iter1 | Iter1 | Phung Kim Manh | Done | II. 2.10 UC-10_User Profile | III. 1.2 f. User Profile | UserProfile.jsp UserProfile.java CustomerDAO.java Customer.java | F1: 'This is a pop-up screen which allows the user to edit his/her profile information, including the registered ones & the avatar image. F2: Please note that s/he is not allowed to change the email | F1: Làm đúng yêu cầu. F2: Làm đúng yêu cầu. | Phung Kim Manh | https://youtu.be/THiTbSt5Bro https://youtu.be/Fb35zZyT2Tc
19 | User Authorization | Common | Complex | 240 | Implementation of authorization mechanism in the system, including the specify the role of logged-in user, his/her authorized page links (building the displayed menu items (in the front end) and preventing unauthorized access via enter the links directly) |  |  | Iter3 | Iter3 | Le Viet Hoang | Done | Done | Done | web.xml package Filter bao gồm các class Filter theo role | Implementation of authorization mechanism in the system, F1: including the specify the role of logged-in user, F2: his/her authorized page links (building the displayed menu items (in the front end) F3: and preventing unauthorized access via enter the links directly) | Done | Le Viet Hoang | https://youtu.be/oW2PbnbsMiQ
20 | My Orders | Customer | Simple | 60 | Show the list of user's orders paginatedly + the sider with the product search box, product categories, the latest products, and static contacts/links - Each order include below information: id, ordered date, product (first product name & number of other products if any), total cost, status; - On clicking the link under the order id, user would be redirected to the Order Information page |  |  | Iter2 | Iter2 | Le Viet Hoang | Done | II. 2.21 UC-21_My Orders | III. 1.2.19. My Orders | MyOrder.jsp MyOrderController.java DAO.java OrderUpdatePagingController.java Order.java OrderDetail.java OrderNumbProduct.java | F1: 'Show the list of user's orders paginatedly F2: + the sider with the product search box, product categories, the latest products, and static contacts/links F3: - Each order include below information: id, ordered date, product (first product name & number of other products if any), total cost, status; F4: - On clicking the link under the order id, user would be redirected to the Order Information page | F1: Pass F2: Pass F3: Pass F4: Pass | Le Viet Hoang | https://youtu.be/hh9Fk_6GoKc
21 | Order Information | Customer | Medium | 120 | Show the order details, including the information as below + the sider with the product search box, product categories, the latest products, and static contacts/links - The order id, order date, total cost, status - The receiver information: full name, gendar, email, mobile - This list of ordered products, each product include following information & the links/buttons that allow the user to re-buy or feedback: thumbnail, name, category, unit price, quantity, total cost For the submitted orders, the user can choose to update (redirect the user to the Cart Details page for that) or cancel the order |  |  | Iter 3 | Iter3 | Phùng Kim Mạnh | Done | II.2.39 UC-39. Order Information | III. 27.Order Information | OrderInformation.java Orderinformation.jsp OrderDAO.java Order.java | F1: 'Show the order details, including the information as below F2: + the sider with the product search box, product categories, the latest products, and static contacts/links F3: - The order id, order date, total cost, status F4: - The receiver information: full name, gendar, email, mobile F5: - This list of ordered products, F6: each product include following information : thumbnail, name, category, unit price, quantity, total cost F7: & the links/buttons that allow the user to re-buy or feedback F8: For the submitted orders, the user can choose to update (redirect the user to the Cart Details page for that) or cancel the order | F1:Pass F2: Pass F3: Pass F4: Pass F5: Pass | Phung Kim Manh | https://youtu.be/w3UFla-M0-g
22 | MKT Dashboard | Marketing | Simple | 60 | Show statistics of posts, products, customers, feedbacks & the trend of new customers by day for the last 7 days (the start date & end date can be adjustable) |  |  | iter3 | iter3 | Nguyen Huu Hieu | Done | II. 2.31 UC-31_Marketer Dashboard | III. 25. Marketing Dashboard | MktDashboardController.java DAO.java dashboard.jsp | F1: 'Show statistics of posts, products, customers, feedbacks F2: & the trend of new customers by day for the last 7 days F3: (the start date & end date can be adjustable) | F1: pass F2: pass F3: pass | HieuNH | https://youtu.be/FaqXzFj9DW8
23 | Posts List | Marketing | Medium | 120 | Show the paginated list of posts (include posts' id, thumbnail, title, category, author, featured, and status information): - The user can filter the post by category, author, status or search by title - Sortable by title, category, author, featured, or status - From each post, the user can choose to hide, show, view, edit it - The page also have the button/link that allows the user to add new post |  |  | Iter2 | Iter2 | Phung Kim Manh | Done | II.2.20 UC_20_PostList(Marketer) | III/1.2/12.PostList | postlist.jsp -addpost.jsp -postlist.java -addpost.java -blogDAO.java Blogs.java Category.java | F1: 'Show the paginated list of posts (include posts' id, thumbnail, title, category, author, featured, and status information): F2: - The user can filter the post by category, author, status or search by title F3: - Sortable by title, category, author, featured, or status F4: - From each post, the user can choose to hide, show, view, edit it F5: - The page also have the button/link that allows the user to add new post | F1:Pass F2: pass F3:pass F4: pass F5: pass | ManhPK | https://youtu.be/wAErRiZuz9c
24 | Post Details | Marketing | Medium | 120 | Show detailed post information (thumbnail, category, title, brief information, description, flag to turn the featurning on/off, status), from that allow the user to input, view or edit them |  |  | Iter2 | Iter2 | Phung Kim Manh | Done | II.2.21 UC_21_Post Detail(Marketer) | III/1.2/13.Post Detail | postdetail.jsp postdetail.java blogDAO.java Blogs.java | F1: 'Show detailed post information (thumbnail, category, title, brief information, description, flag to turn the featurning on/off, status), F2: from that allow the user to input, view or edit them | F1: pass F2: pass | ManhPK | https://youtu.be/mWi5hiuBSzU
25 | Sliders List | Marketing | Simple | 60 | Show the paginated list of sliders (including sliders' id, title, image, backlink, status) - The user can filter the sliders by the status + search by title or backlink - User can navigate to slider detail by clicking each slider |  |  | Iter2 | Iter2 | DungNV | Done | II. 2.1 UC-14_Slider List (Marketer) | III/1.2/ 14. Slider List | sliderList.jsp MKTSliderListController.java SliderListDAO.java Slider.java | F1: 'Show the paginated list of sliders (including sliders' id, title, image, backlink, status) F2: - The user can filter the sliders by the status + search by title or backlink F3: User can navigate to slider detail by clicking each slider | F1: pass F2: pass F3: pass | DungNV | https://www.youtube.com/watch?v=I-Sk0Utjy3I
26 | Slider Details | Marketing | Simple | 60 | Show detailed slider information (image, title, backlink, status, notes) For each slider, the user can choose to hide, show, edit it |  |  | Iter2 | Iter2 | Phung Kim Manh | Done | II.2.1 UC_22_Slider Detail(Marketer) | III/1.2/15/Slider Detail | sliderdetail.jsp sliderDetail.java BlogDAO.java slider.java | F1: 'Show detailed slider information (image, title, backlink, status, notes) F2: For each slider, the user can choose to hide, show, edit it | F1: passs F2:pass | ManhPK | https://youtu.be/FoE_QNY17pQ
27 | Products List | Marketing | Medium | 120 | Show the paginated list of products (include products' id, thumbnail, title, category, list price, sale price, featured, and status information): - The user can filter the product by category, status or search by title, brief info - Sortable by title, category, list price, sale price, featured, or status - From each product, the user can choose to hide, show, view, edit it - The page also have the button/link that allows the user to add new product |  |  | Iter2 | Iter2 | Nguyen Huu Hieu | Done | II. 2.13 UC-13_Product List (Marketer) | III 1.2.11. Product List (Marketer) | MktProductListController.java DAO.java product-list.jsp | F1: 'Show the paginated list of products (include products' id, thumbnail, title, category, list price, sale price, featured, and status information): F2: - The user can filter the product by category, status or search by title, brief info F3: - Sortable by title, category, list price, sale price, featured, or status F4: - From each product, the user can choose to hide, show, view, edit it F5: - The page also have the button/link that allows the user to add new product | F1: pass F2: pass F3: pass F4: pass F5: pass | HieuNH | https://youtu.be/Sh8RTajc9zE
28 | Product Details | Marketing | Medium | 120 | Show detailed product information (thumbnail, category, title, brief information, attached images, description, quantity, list price, sale price, flag to turn the featurning on/off, status), from that allow the user to input, view or edit them |  |  | Iter2 | Iter2 | Nguyen Huu Hieu | Done | II. 2.16 UC-16_Product Details(Marketer) | III 1.2.16. Product Detail (Marketer) | MktProductDetailController.java DAO.java product-detail.jsp | F1: 'Show detailed product information (thumbnail, category, title, brief information, attached images, description, quantity, list price, sale price, flag to turn the featurning on/off, status), F2: from that allow the user to input, view or edit them | F1: pass F2: pass | HieuNH | https://youtu.be/32TGivFFCoY
29 | Add Product | Marketing | Simple | 60 | Add new product information(category, name, original price, sale price, thumbnail, product image,color, size, bref information, description, number left, status) |  |  | Iter2 | Iter2 | Nguyen Huu Hieu | Done | II. 2.17 UC-17_Add Product (Marketer) | III 1.2.20. Add Product (Marketer) | MktAddProductController.java DAO.java add-productjsp | F1: 'Show new product information(category, name, original price, sale price, thumbnail, product image,color, size, bref information, description, number left, status) to input F2: from that allow the user to add new product | F1: pass F2: pass | HieuNH | https://youtu.be/7hBkbTfJgp0
30 | Payment | Customer | Medium | 120 | Payment via VNPay, Credit Card |  |  | Iter2 | Iter2 | Nguyen Huu Hieu | Done | II. 2.18 UC-18_Payment | III 1.2.23. Payment | PaymentController.java DAO.java CartContact.jsp | F1: 'Show payment method(COD/VNPAYQR/CreditCard F2: from that allow the customer to paymnet order | F1: pass F2: pass | HieuNH | https://youtu.be/3XpAc8OgDEI
31 | Customers List | Marketing | Simple | 60 | Show the list of customers / contacts paginatedly (include contacts' id, full name, gender, email, mobile, status): - The user can filter the customers by status + search by full name, email, mobile - Sortable by full name, email, mobile, status - From each customer, the user can choose to add new, view or edit it |  |  | iter3 | iter3 | Nguyen Huu Hieu | Done | II. 2.32 UC-32_Customer List | III. 26. Customers List | MktCustomerListController.java CustomerDAO.java customer-list.jsp | F1: 'Show the list of customers / contacts paginatedly (include contacts' id, full name, gender, email, mobile, status): F2: - The user can filter the customers by status F3: + search by full name, email, mobile F4: - Sortable by full name, email, mobile, status F5: - From each customer, the user can choose to add new, view or edit it Note: Chỉ cho phép marketer view and update status, not add new and edit customer information. | F1: done F2: done F3: done F4: done F5:done | HieuNH | https://youtu.be/kQGJ94CLaWw
32 | Customer Details | Marketing | Simple | 60 | Show detailed customer/contact information (full name, gender, email, mobile, address, status), from that allow the user to input, view or edit them (excep for the status which is generated automatically - contact, potential or customer) Besides, the screen also shows the list of customer/contact changes history in the form of a table which includes following columns: email, full-name, gender, mobile, address, updated by, updated date |  |  | iter3 | iter3 | Nguyen Huu Hieu | Done | II. 2.33 UC-33_Customer Detail | III. 28. Customer Details | customer-detail.jsp MktCustomerDetail.java OrderDAO.java | F1: 'Show detailed customer/contact information (full name, gender, email, mobile, address, status), F2: from that allow the user to input, view or edit them (except for the status which is generated automatically - contact, potential or customer) Note: status chỉ bao gồm active/inactive customer F3: Besides, the screen also shows the list of customer/contact changes history in the form of a table which includes following columns: email, full-name, gender, mobile, address, updated by, updated date | F1: done F2:done F3:not yet | HieuNH | https://youtu.be/h5DMufUdKPA
33 | Feedbacks List | Marketing | Medium | 120 | Show the list of feedbacks paginatedly (include feedbacks' contact full name, product name, rated star, status): - The user can filter the feedbacks by status, product, rated star + search by full name, feedback content - Sortable by full name, product name, rated star, status - From each feedback, the user can choose to view or change it's status |  |  | Iter3 | Iter3 | ManhPK | done | II.2.29 UC-29_FeedBackList | III. 1.2.24. FeedBackList | feedbackList.jsp feedbackList.jsp feedbackDAO FeedBacks | F1: 'Show the list of feedbacks paginatedly (include feedbacks' contact full name, product name, rated star, status): F2: - The user can filter the feedbacks by status, product, rated star F3: + search by full name, feedback content F4:- Sortable by full name, product name, rated star, status F5: - From each feedback, the user can choose to view or change it's status | F1: done F2: done F3: done F4: done | ManhPK | https://youtu.be/MDdpsDJxnEA
34 | Feedback Details | Marketing | Simple | 60 | Show the feedback details (contact full name, email, mobile, product, rated star, feedback) from that allow the user to change its status |  |  | Iter3 | Iter3 | ManhPK | done | II.2.30 UC-30_FeedBackDetail | III. 2.2.36. Feedback DEtail | feedbackDetail.jsp feedbackDetail.java feedbackDAO FeedBacks | F1: 'Show the feedback details (contact full name, email, mobile, product, rated star, feedback, images status) from that allow the user to change its status Note: Chức năng này chỉ 60 LOC | F1: done | ManhPK | https://youtu.be/m1x46-5TNVI
35 | Sale Dashboard | Sale | Medium | 120 | Show the trend of success/total orders, and the revenues trends by day for the last 7 days for all or a specific sale person (the start date, end date, sale, order status can be adjustable) |  |  | Iter3 | Iter3 | DungNV | done | II. 2.25 UC-25_Sale dashboard (Seller) | III 1.2.35. Sale dashboard (Seller) | OrderCount.java SaleDashboardDAO.java SaleDashboardController.java sale-dashboard.jsp | F1: 'Show the trend of success/total orders, F2: and the revenues trends F3: by day for the last 7 days for all or a specific sale person (the start date, end date, sale, order status can be adjustable) Note: These trends should be shown by bar chart. In that case it will be considered as a Medium function ~ 120 LOC | F1: Pass F2: Pass F3: Pass | DungNV | https://youtu.be/D7JYBGbVB2M
36 | Orders List | Sale | Simple | 60 | Show the list of orders paginatedly - The list can be shorted by the order date, customer name, total cost, status - Each order include below information: id, ordered date, customer name, product (first product name & number of other products if any), total cost, status; - Allow the users to filter the order by the order date (from, to), sale name, status - Allow the user to search the orders by order id, customer name - On clicking the link under the order id, user would be redirected to the Order Details page |  |  | Iter2 | Iter3 | DungNV | done | II. 2.23 UC-23_Order list (Seller) | III 1.2.33. Order list (Seller) | Order.java OrderDetail.java OrderListDAO.java SaleOrderListController.java SaleEmployeeOrderListController.java order-list.jsp sale-employee-order-list.jsp | F1: 'Show the list of orders paginatedly F2: - The list can be shorted by the order date, customer name, total cost, status F3: - Each order include below information: id, ordered date, customer name, product (first product name & number of other products if any), total cost, status; F4: - Allow the users to filter the order by the order date (from, to), sale name, status F5: - Allow the user to search the orders by order id, customer name F6: - On clicking the link under the order id, user would be redirected to the Order Details page | F1: Pass F2: Pass F3: Pass F4: Pass F5: Pass F6: Pass | DungNV | https://youtu.be/Ayyo_8B9coE
37 | Order Details | Sale | Medium | 120 | Show the order details, including the following information: - Basic order information: order id, customer full name, email, mobile, order date, total cost, sale name, status - The receiver information: full name, gendar, email, mobile, address - This list of ordered products, each product include following information: thumbnail, name, category, unit price, quantity, total cost Sale Manager & the assigned Sale can change the order status & the sale notes Sale Manager can assign the order to other sale |  |  | Iter2 | Iter3 | DungNV | done | II. 2.24 UC-24_Sale detail (Seller) | III 1.2.34. Sale detail (Seller) | Order.java OrderDetail.java OrderDetailDAO.java SaleOrderDetailController_new.java SaleManagerOrderDetailController.java sale-order-detail.jsp sale-employee-order-detail.jsp | 'Show the order details, including the following information: F1: - Basic order information: order id, customer full name, email, mobile, order date, total cost, sale name, status F2: - The receiver information: full name, gendar, email, mobile, address F3: - This list of ordered products, each product include following information: thumbnail, name, category, unit price, quantity, total cost F4: Sale Manager & the assigned Sale can change the order status & the sale notes F5: Sale Manager can assign the order to other sale Notes: This function shoud be considered as a Medium function | F1: Pass F2: Pass F3: Pass F4: Pass F5: Pass | DungNV | https://youtu.be/-H2Yl8sM9Vk
38 | Product List | Warehouser | Simple | 60 | Show the products paginatedly - Shown product information includes its thumbnail, title, brief information, original price, and sale price, category, hold, quantity, status - The user is redirected to the product's details on his/her clicking on the product |  |  | Iter3 | Iter3 | HieuNH | done | II. 2.38 UC-38_Product List | III. 1.2.39: Product List | Product.java ProductDAO.java WarehouserProductListController.java warehouser-product-list.jsp | F1: Show the products paginatedly F2: - Shown product information includes its thumbnail, title, brief information, original price, and sale price, category, hold, quantity, status F3: - The user is redirected to the product's details on his/her clicking on the product | F1: pass F2: pass F3: pass | HieuNH | https://youtu.be/_bZF0pcXPiI
39 | Import Product | Warehouser | Simple | 60 | Show the products need input - Shown product information input includes its product size, color, import price - The user is click add new product will save data to database |  |  | Iter3 | Iter3 | HieuNH | done | II. 2.40 UC-40_Import Product | III. 1.2.41: Import Product | Product.java ProductDAO.java WarehouserImportProductController.java import-product.jsp | F1: Shown product information input includes its product size, color, import price F2: - The user is click add new product will save data to database | F1: pass F2: pass | HieuNH | https://youtu.be/_bZF0pcXPiI
40 | Admin Dashboard | Admin | Medium | 120 | Show statistics of new orders (success, cancelled, submitted), revenues (total, by product categories), customers (newly registered, newly bought), feedbacks (average star: total, by product categories) & the trend of order counts (success, all) by day for the last 7 days (the start date & end date can be adjustable) |  |  | Iter3 | Iter3 | Le Viet Hoang | done | II. 2.26 UC-26_Admin Dashboard | III. 2.30 UC-30_Admin Dashboard | HomeController.java admin/home.jsp | F1: 'Show statistics of new orders (success, cancelled, submitted), F2: revenues (total, by product categories), F3: customers (newly registered, newly bought), F4: feedbacks (average star: total, by product categories) F5: & the trend of order counts (success, all) All: by day for the last 7 days (the start date & end date can be adjustable) This should be considered as Medium function | F1: Pass F2: Pass F3: Pass F4: Pass F5: Pass | Le Viet Hoang | https://youtu.be/hK1-fmxKHnY
41 | Users List | Admin | Simple | 60 | Show the paginated list of registered users (include users' id, full name, gender, email, mobile, role, status): - The admin can filter the users by gender, role, status - Allow the admin to seach users by full name, email, mobile - The list is sortable by id, fullname, gender, email, mobile, role, status - From each user, the admin can choose to view or edit it - The page also have the button/link that allows the admin to add new user |  |  | Iter3 | Iter3 | Le Viet Hoang | done | II. 2.27 UC-27_User List | III. 2.31 UC-31_User List | UserListController.java NewEmployeeController.java admin/userlist.jsp admin/newemployee.jsp | F1: 'Show the paginated list of registered users (include users' id, full name, gender, email, mobile, role, status): F2: - The admin can filter the users by gender, role, status F3: - Allow the admin to seach users by full name, email, mobile F4: - The list is sortable by id, fullname, gender, email, mobile, role, status F5: - From each user, the admin can choose to view or edit it F6:- The page also have the button/link that allows the admin to add new user | F1: Pass F2: Pass F3: Pass F4: Pass F5: Pass F6 Pass | Le Viet Hoang | https://youtu.be/hK1-fmxKHnY
42 | User Details | Admin | Simple | 60 | Show detailed user information (avatar, full name, gender, email, mobile, role, address, status), from that allow the user to add new, view or edit user information - After adding, new generated login password would be email to the new user - The admin can only edit/update the role and status of the user |  |  | Iter3 | Iter3 | Le Viet Hoang | done | II. 2.28 UC-28_User Details | III. 2.32 UC-32_User Details | UserDetailsController.java admin/userdetails.jsp | F1: 'Show detailed user information (avatar, full name, gender, email, mobile, role, address, status), F2: from that allow the user to add new, view or edit user information F3: - After adding, new generated login password would be email to the new user F4:- The admin can only edit/update the role and status of the user | F1: Pass F2: Pass F3: Pass F4: Pass | Le Viet Hoang | https://youtu.be/hK1-fmxKHnY
43 | Settings List | Admin | Simple | 60 | Show the paginated list of settings (include settings' id, type, value, order, status): - The admin can filter the setting by type, status - Allow the admin to seach settings by value - From each setting, the admin can choose to view, activate/deactivate, or edit it - The page also have the button/link that allows the admin to add new setting |  |  | Iter3 | Iter3 | DungNV | done | II. 2.36 UC-36_Setting List (admin) | III 1.2.38. Setting List (admin) | Category.java CategoryListDAO.java CategoryListController.java CategoryList.jsp | F1: 'Show the paginated list of settings (include settings' id, type, value, order, status): F2: - The admin can filter the setting by type, status F3: - Allow the admin to seach settings by value F4: - From each setting, the admin can choose to view, activate/deactivate, or edit it F5: - The page also have the button/link that allows the admin to add new setting | F1:pass F2: pass F3:pass F4: pass F5: pass F6: pass | DungNV | https://youtu.be/wc_FKybfH28
44 | Setting Details | Admin | Simple | 60 | Show detailed user information (type, value, order, description, status), from that allow the user to add new, view or edit setting information |  |  | Iter3 | Iter3 | DungNV | done | II. 2.37 UC-37_Setting detail (admin) | III 1.2.38. Setting detail (admin) | Category.java CategoryListDAO.java CategoryDetailController.java NewCategoryController.java CategoryDetail.jsp newCategory.jsp | F1: 'Show detailed user information (type, value, order, description, status), F2: from that allow the user to add new, view or edit setting information | F1: pass F2: pass | DungNV | https://youtu.be/zM_2VxPDUX4

## CartDetails
TEST CASES FOR CART DETAILS SCREEN
CREATE TEST CASE | [6 empty] | Excution |  |  |  | Fixing Bug |  |  |  | Confirmation Check
Functional Requirement (URD) | Sub Requirement | Test Case ID | Test case Description | Expected output | Type | Create By | Actual Output | Tester | Date | Result | PIC | Root course | Solution | Fixed Date | Tester | Confirm Date | Final Confirm
Show the cart details with list of the user's chosen products (including Id, title, price, quantity, total cost) and the total order price + the sider with the product search box, product categories, the latest products, and static contacts/links; The user can - Change the quantity of each product: the total cost is automatically adjusted - Choose to delete/remove product by clicking on the deleting icon - Click the Choose More Product button to go to Products List page - Click the Check Out button to go to the Cart Contact page Please notes: the user's chosen products from the last browsing session are remained in his/her cart until s/he submit the cart. However, the product prices are updated with the latest prices in the system | R1. Show the cart details with list of the user's chosen products (including Id, title, price, quantity, total cost) and the total order price + the sider with the product search box, product categories, the latest products, and static contacts/links | CD-001 | Test screen có đủ thông tin không | Màn hình có đầy đủ thông tin như yêu cầu: Id, title, price, quantity, total cost) and the total order price + the sider with the product search box, product categories, the latest products | Screen layout | Lê Việt Hoàng |  | HoangLV |  | Passed
| R2. Customer can change the quantity of each product: the total cost is automatically adjusted | CD-002 | Nhấn thay đổi số lượng sản phẩm | Số lượng sản phẩm được thay đổi | Abnormal | Lê Việt Hoàng |  | HoangLV |  | Passed
| R3. Customer can choose to delete/remove product by clicking on the deleting icon | CD-003 | Xóa sản phẩm bằng cách nhấn vào icon | Màn hình hiển thị thông báo | Abnormal | Lê Việt Hoàng |  | HoangLV |  | Passed
| R4. Customer can click the Choose More Product button to go to Products List page | CD-004 | Nhấn "Choose More" để chuyển sang trang danh sách sản phẩm | Chuyển hướng màn hình sang màn Product List Page | Abnormal | Lê Việt Hoàng |  | HoangLV |  | Passed
| R5. Customer can click the Check out button to go to Cart Contact page | CD-005 | Nhấn "Check out" để chuyển sang trang Cart Contact | Chuyển hướng màn hình sang màn Cart Contact | Abnormal | Lê Việt Hoàng |  | HoangLV |  | Passed
|  |  | Type | Num of TC
|  |  | Small | 5
|  |  | Medium | 0
|  |  | Complex | 0

## UserList
TEST CASES FOR USER LIST SCREEN
TEST CASES FOR USER LIST SCREEN
| CREATE TEST CASE | [6 empty] | Excution |  |  |  | Fixing Bug |  |  |  | Confirmation Check
| Functional Requirement (URD) | Sub Requirement | Test Case ID | Test case Description | Expected output | Type | Create By | Actual Output | Tester | Date | Result | PIC | Root course | Solution | Fixed Date | Tester | Confirm Date | Final Confirm
| Show the paginated list of registered users (include users' id, full name, gender, email, mobile, role, status): - The admin can filter the users by gender, role, status - Allow the admin to seach users by full name, email, mobile - The list is sortable by id, fullname, gender, email, mobile, role, status - From each user, the admin can choose to view or edit it - The page also have the button/link that allows the admin to add new user | F1: Show the list of users paginatedly | UserList-001 | Test screen có show theo page hay không và đủ thông tin theo yêu cầu hay không | Test screen có show theo page và đủ thông tin theo yêu cầu | Screen layout | HoangLV | Test screen có show theo page và đủ thông tin theo yêu cầu | HoangLV | 2024-10-19 | Passed
|  | F2: - The list can be id, fullname, gender, email, mobile, role, status | UserList-002 | Data có thể sort theo các cột id, fullname, gender, email, mobile, role, status hay không | Data có thể sort theo các cột id, fullname, gender, email, mobile, role, status | Screen function | HoangLV | Data có thể sort theo các cột id, fullname, gender, email, mobile, role, status | HoangLV | 2024-10-19 | Passed
|  | F3: - Each order include below information: users' id, full name, gender, email, mobile, role, status | UserList-003 | Các thông tin show ra ở bảng có đủ các trường cần thiết hay không | Các thông tin show ra ở bảng có đủ các trường cần thiết | Screen function | HoangLV | Các thông tin show ra ở bảng có đủ các trường cần thiết | HoangLV | 2024-10-19 | Passed
|  | F4: - Allow the users to filter the users by gender, role, status | UserList-004 | Có thể tìm kiếm đc thông tin theo users by gender, role, status | Có thể tìm kiếm đc thông tin theo users by gender, role, status | Screen function | HoangLV | Có thể tìm kiếm đc thông tin theo users by gender, role, status | HoangLV | 2024-10-19 | Passed
|  | F5: - Allow the user to search users by full name, email, mobile | UserList-005 | Có thể tìm kiếm đc thông tin theo full name, email, mobile | Có thể tìm kiếm đc thông tin theo full name, email, mobile | Screen function | HoangLV | Có thể tìm kiếm đc thông tin theo full name, email, mobile | HoangLV | 2024-10-19 | Passed
|  | F6: - On clicking the link that allows the admin to add new user | UserList-006 | Có add thành công không | Có add thành công | Screen function | HoangLV | Có add thành công | HoangLV | 2024-10-19 | Passed
[5 empty] | Type | Num of TC
[5 empty] | Small | 0
[5 empty] | Medium | 6
[5 empty] | Complex | 0

## UserDetails
TEST CASES FOR USER DETAIL SCREEN
TEST CASES FOR USER DETAIL SCREEN
| CREATE TEST CASE | [6 empty] | Excution |  |  |  | Fixing Bug |  |  |  | Confirmation Check
| Functional Requirement (URD) | Sub Requirement | Test Case ID | Test case Description | Expected output | Type | Create By | Actual Output | Tester | Date | Result | PIC | Root course | Solution | Fixed Date | Tester | Confirm Date | Final Confirm
| Show detailed user information (avatar, full name, gender, email, mobile, role, address, status), from that allow the user to add new, view or edit user information - After adding, new generated login password would be email to the new user - The admin can only edit/update the role and status of the user | F1: - detailed user information (avatar, full name, gender, email, mobile, role, address, status) | UserDetails-001 | Test screen có show đủ thông tin theo yêu cầu hay không | Test screen có show đủ thông tin theo yêu cầu | Screen layout | HoangLV | Test screen có show đủ thông tin theo yêu cầu | HoangLV | 2024-10-19 | Passed
|  | F2: - allow the user to add new, view or edit user information | UserDetails-002 | cho phép admin add, view, edit user information không | cho phép admin add, view, edit user information | Screen function | HoangLV | cho phép admin add, view, edit user information | HoangLV | 2024-10-19 | Passed
|  | F3: - After adding, new generated login password would be email to the new user | UserDetails-003 | Gửi mail sau khi tạo login password mới hay không | Gửi mail sau khi tạo login password mới | Screen function | HoangLV | Gửi mail sau khi tạo login password mới | HoangLV | 2024-10-19 | Passed
[5 empty] | Type | Num of TC
[5 empty] | Small | 0
[5 empty] | Medium | 3
[5 empty] | Complex | 0

## PostList
TEST CASES FOR SALE DASHBOARD SCREEN
TEST CASES FOR SALE DASHBOARD SCREEN
| CREATE TEST CASE | [6 empty] | Excution |  |  |  | Fixing Bug |  |  |  | Confirmation Check
| Functional Requirement (URD) | Sub Requirement | Test Case ID | Test case Description | Expected output | Type | Create By | Actual Output | Tester | Date | Result | PIC | Root course | Solution | Fixed Date | Tester | Confirm Date | Final Confirm
| Show the paginated list of posts (include posts' id, thumbnail, title, category, author, featured, and status information): - The user can filter the post by category, author, status or search by title - Sortable by title, category, author, featured, or status - From each post, the user can choose to hide, show, view, edit it - The page also have the button/link that allows the user to add new post | F1: 'Show the paginated list of posts (include posts' id, thumbnail, title, category, author, featured, and status information): F2: - The user can filter the post by category, author, status or search by title F3: - Sortable by title, category, author, featured, or status F4: - From each post, the user can choose to hide, show, view, edit it F5: - The page also have the button/link that allows the user to add new post | Marketer-001 Marketer-002 Marketer-003 Marketer-004 Marketer-004 | Hiển thị những thông tin yêu cầu filter theo category, status có thể thay đổi trạng thái có đường dẫn để thêm 1 trang addpost | Test screen có show đủ thông tin theo yêu cầu Có filter được không có thể thay đổi status không có nút thêm bài mới không | Screen layout | ManhPK | Test screen có show đủ thông tin theo yêu cầu | ManhPK |  | Passed Passed Passed Passed
[5 empty] | Type | Num of TC
[5 empty] | Small | 0
[5 empty] | Medium | 3
[5 empty] | Complex | 0

## PostDetail
TEST CASES FOR SALE DASHBOARD SCREEN
TEST CASES FOR SALE DASHBOARD SCREEN
| CREATE TEST CASE | [6 empty] | Excution |  |  |  | Fixing Bug |  |  |  | Confirmation Check
| Functional Requirement (URD) | Sub Requirement | Test Case ID | Test case Description | Expected output | Type | Create By | Actual Output | Tester | Date | Result | PIC | Root course | Solution | Fixed Date | Tester | Confirm Date | Final Confirm
| Show detailed post information (thumbnail, category, title, brief information, description, flag to turn the featurning on/off, status), from that allow the user to input, view or edit them | F1: 'Show detailed post information (thumbnail, category, title, brief information, description, flag to turn the featurning on/off, status), F2: from that allow the user to input, view or edit them | Marketer-001 Marketer-002 | Hiển thị những thông tin yêu cầu Có thể chỉnh sửa | Test screen có show đủ thông tin theo yêu cầu có chỉnh sửa được không | Screen layout | ManhPK | Test screen có show đủ thông tin theo yêu cầu | ManhPK |  | Passed Passed
[5 empty] | Type | Num of TC
[5 empty] | Small | 0
[5 empty] | Medium | 3
[5 empty] | Complex | 0

## SliderDetail
TEST CASES FOR SALE DASHBOARD SCREEN
TEST CASES FOR SALE DASHBOARD SCREEN
| CREATE TEST CASE | [6 empty] | Excution |  |  |  | Fixing Bug |  |  |  | Confirmation Check
| Functional Requirement (URD) | Sub Requirement | Test Case ID | Test case Description | Expected output | Type | Create By | Actual Output | Tester | Date | Result | PIC | Root course | Solution | Fixed Date | Tester | Confirm Date | Final Confirm
| Show detailed slider information (image, title, backlink, status, notes) For each slider, the user can choose to hide, show, edit it | F1: 'Show detailed slider information (image, title, backlink, status, notes) F2: For each slider, the user can choose to hide, show, edit it | Marketer-001 Marketer-002 | Hiển thị những thông tin yêu cầu Có thể chỉnh sửa | Test screen có show đủ thông tin theo yêu cầu có chỉnh sửa được không | Screen layout | ManhPK | Test screen có show đủ thông tin theo yêu cầu | ManhPK |  | Passed Passed
[5 empty] | Type | Num of TC
[5 empty] | Small | 0
[5 empty] | Medium | 3
[5 empty] | Complex | 0

## AdminDashboard
TEST CASES FOR SALE DASHBOARD SCREEN
TEST CASES FOR SALE DASHBOARD SCREEN
| CREATE TEST CASE | [6 empty] | Excution |  |  |  | Fixing Bug |  |  |  | Confirmation Check
| Functional Requirement (URD) | Sub Requirement | Test Case ID | Test case Description | Expected output | Type | Create By | Actual Output | Tester | Date | Result | PIC | Root course | Solution | Fixed Date | Tester | Confirm Date | Final Confirm
| Show statistics of new orders (success, cancelled, submitted), revenues (total, by product categories), customers (newly registered, newly bought), feedbacks (average star: total, by product categories) & the trend of order counts (success, all) by day for the last 7 days (the start date & end date can be adjustable) | F1: hiển thị đầy đủ thông tin không | AdminDashboard-001 | F1: hiển thị đầy đủ thông tin không | F1: hiển thị đầy đủ thông tin | Screen layout | HoangLV | Test screen có show đủ thông tin theo yêu cầu | HoangLV | 2024-10-19 | Passed
|  | F2: and the revenues trends | AdminDashboard-002 | Test screen có show được chart cho revenue hay không | Test screen có show được chart cho revenue | Screen layout | HoangLV | Test screen có show được chart cho revenue | HoangLV | 2024-10-19 | Passed
|  | F3:the trend of order counts (success, all) by day for the last 7 days(the start date & end date can be adjustable) | AdminDashboard-003 | Có thể filter chart theo start date, end date hay không | Có thể filter chart theo start date, end date, sale | Screen function | HoangLV | Có thể filter chart theo start date, end date, sale | HoangLV | 2024-10-19 | Passed
[5 empty] | Type | Num of TC
[5 empty] | Small | 0
[5 empty] | Medium | 3
[5 empty] | Complex | 0

## CartContact
TEST CASES FOR CART CONTACT SCREEN
CREATE TEST CASE | [6 empty] | Excution |  |  |  | Fixing Bug |  |  |  | Confirmation Check
Functional Requirement (URD) | Sub Requirement | Test Case ID | Test case Description | Expected output | Type | Create By | Actual Output | Tester | Date | Result | PIC | Root course | Solution | Fixed Date | Tester | Confirm Date | Final Confirm
Show the list of user chosen product (including id, title, price, quantity, total cost), the total order price and the receiver information (including full-name, gender, email, mobile, address, notes) for user to edit/input + the sider with the product search box, product categories, the latest products, and static contacts/links - In case the user has logged in, the receiver information would be filled with the user's information - The user can click the Change button to come back to the Cart Details page for changing the choosing products, click the Submit button to submit the order before redirecting user to the Card Completion or Error page (due to technical error or any out-of-stock product) | R1. Show the list of user chosen product (including id, title, price, quantity, total cost), the total order price and the receiver information (including full-name, gender, email, mobile, address, notes) for user to edit/input + the sider with the product search box, product categories, the latest products, and static contacts/links | PD-001 | Test screen có đủ thông tin không | Màn hình có đầy đủ thông tin như yêu cầu: id, title, price, quantity, total cost), the total order price and the receiver information (including full-name, gender, email, mobile, address, notes) for user to edit/input + the sider with the product search box, product categories, the latest product | Screen layout | Lê Việt Hoàng |  | HoangLV |  | Passed
| R2. In case the user has logged in, the receiver information would be filled with the user's information | PD-002 | Hiển thị thông tin tương ứng đã đăng kí | Hiển thị thông tin tương ứng đã đăng kí | Abnormal | Lê Việt Hoàng |  | HoangLV |  | Passed
| R3. Customer can click the Change button to come back to the Cart Details page for changing the choosing products | PD-003 | Nhấn "Change" để quay lại trang Cart Details để chọn sản phẩm | Chuyển hướng màn hình sang màn Cart Details | Abnormal | Lê Việt Hoàng |  | HoangLV |  | Passed
| R4. Customer can click the Submit button to submit the order before redirecting user to the Card Completion or Error page (due to technical error or any out-of-stock product) | PD-004 | Nhấn "Submit" để chốt sản phẩm đã lựa chọn | Chuyển hướng màn hình sang màn Card Completion or Error page (due to technical error or any out-of-stock product) | Abnormal | Lê Việt Hoàng |  | HoangLV |  | Passed
|  |  | Type | Num of TC
|  |  | Small | 4
|  |  | Medium | 0
|  |  | Complex | 0

## MyOrders
TEST CASES FOR MY ORDERS SCREEN
CREATE TEST CASE | [6 empty] | Excution |  |  |  | Fixing Bug |  |  |  | Confirmation Check
Functional Requirement (URD) | Sub Requirement | Test Case ID | Test case Description | Expected output | Type | Create By | Actual Output | Tester | Date | Result | PIC | Root course | Solution | Fixed Date | Tester | Confirm Date | Final Confirm
Show the list of user's orders paginatedly + the sider with the product search box, product categories, the latest products, and static contacts/links - Each order include below information: id, ordered date, product (first product name & number of other products if any), total cost, status; - On clicking the link under the order id, user would be redirected to the Order Information page | R1. Show the list of user's orders paginatedly + the sider with the product search box, product categories, the latest products, and static contacts/links | PD-001 | Test screen có đủ thông tin không | Màn hình có đầy đủ thông tin | Screen layout | Lê Việt Hoàng |  | HoangLV |  | Passed
| R2. Each order include below information: id, ordered date, product (first product name & number of other products if any), total cost, status; | PD-002 | Hiển thị thông tin : id, ordered date, product (first product name & number of other products if any), total cost, status; | Hiển thị thông tin tương ứng | Abnormal | Lê Việt Hoàng |  | HoangLV |  | Passed
| R3. Customer can click the View Order Details button to redirect to Order Information page | PD-003 | Nhấn "View Order Details" để chuyển sang trang Order Information | Chuyển hướng màn hình sang màn Order Information | Abnormal | Lê Việt Hoàng |  | HoangLV |  | Passed
|  |  | Type | Num of TC
|  |  | Small | 3
|  |  | Medium | 0
|  |  | Complex | 0

## Issue Log
Bug ID | Bug Description | Function/Screen Name | Sprint | PIC | Open Date | Deadline | Reviewer | Review Date | Status

## FeedBack LIst
TEST CASES FOR SALE DASHBOARD SCREEN
TEST CASES FOR SALE DASHBOARD SCREEN
| CREATE TEST CASE | [6 empty] | Excution |  |  |  | Fixing Bug |  |  |  | Confirmation Check
| Functional Requirement (URD) | Sub Requirement | Test Case ID | Test case Description | Expected output | Type | Create By | Actual Output | Tester | Date | Result | PIC | Root course | Solution | Fixed Date | Tester | Confirm Date | Final Confirm
| Show the list of feedbacks paginatedly (include feedbacks' contact full name, product name, rated star, status): - The user can filter the feedbacks by status, product, rated star + search by full name, feedback content - Sortable by full name, product name, rated star, status - From each feedback, the user can choose to view or change it's status | F1: 'Show the list of feedbacks paginatedly (include feedbacks' contact full name, product name, rated star, status): F2: - The user can filter the feedbacks by status, product, rated star F3: + search by full name, feedback content F4:- Sortable by full name, product name, rated star, status F5: - From each feedback, the user can choose to view or change it's status | Marketer-001 Marketer-002 Marketer-003 Marketer-004 | Hiển thị những thông tin yêu cầu filter theo status, rated_star search theo tên sản phẩm có thể thay đổi trạng thái | Test screen có show đủ thông tin theo yêu cầu Có filter được không có tìm kiếm được không có thể thay đổi status không | Screen layout | ManhPK | Test screen có show đủ thông tin theo yêu cầu | ManhPK | 2024-10-19 | Passed Passed Passed Passed
[5 empty] | Type | Num of TC
[5 empty] | Small | 0
[5 empty] | Medium | 3
[5 empty] | Complex | 0

## FeedBack Detail
TEST CASES FOR SALE DASHBOARD SCREEN
TEST CASES FOR SALE DASHBOARD SCREEN
| CREATE TEST CASE | [6 empty] | Excution |  |  |  | Fixing Bug |  |  |  | Confirmation Check
| Functional Requirement (URD) | Sub Requirement | Test Case ID | Test case Description | Expected output | Type | Create By | Actual Output | Tester | Date | Result | PIC | Root course | Solution | Fixed Date | Tester | Confirm Date | Final Confirm
| Show the feedback details (contact full name, email, mobile, product, rated star, feedback) from that allow the user to change its status | F1: 'Show the feedback details (contact full name, email, mobile, product, rated star, feedback, images status) from that allow the user to change its status | Marketer-001 | Hiển thị những thông tin yêu cầu có thể thay đổi trạng thái | Test screen có show đủ thông tin theo yêu cầu có thể thay đổi status không | Screen layout | ManhPK | Test screen có show đủ thông tin theo yêu cầu | ManhPK | 2024-10-19 | Passed
[5 empty] | Type | Num of TC
[5 empty] | Small | 0
[5 empty] | Medium | 3
[5 empty] | Complex | 0

## Login
TEST CASES FOR LOGIN SCREEN
CREATE TEST CASE | [6 empty] | Excution |  |  |  | Fixing Bug |  |  |  | Confirmation Check
Functional Requirement (URD) | Sub Requirement | Test Case ID | Test case Description | Expected output | Type | Create By | Actual Output | Tester | Date | Result | PIC | Root course | Solution | Fixed Date | Tester | Confirm Date | Final Confirm
Allows the user to enter email & password to login; on this page, there are also options for user to register new information or reset the password for the case s/he forget it | R1. Allows the user to enter email & password to login; on this page, there are also options for user to register new information or reset the password for the case s/he forget it | LOG-IN-001 | Test screen có đủ thông tin không | Màn hình có đầy đủ thông tin như yêu cầu: email, password, Login button, Forgot password | Screen layout | Nguyen Huu Hieu |  | HieuNH | 2024-09-20 | Passed
| R2. After user click Login button, the Online Shop system will redirect to Home Page | LOG-IN-002 | B1: Gọi màn hình Login từ Home Page hoặc url /login B2: Nhập thông tin đúng email với password và click Login button | - User được đưa đến màn hình home ở trạng thái đã login | Abnormal | Nguyen Huu Hieu |  | HieuNH | 2024-09-20 | Passed
|  | LOG-IN-003 | B1: User input incorrect format email: hieunh@, hieunh@gm | Hệ thống thông báo Vui lòng bao gồm @ | Abnormal | Nguyen Huu Hieu | System display: Vui lòng bao gồm @... | HieuNH | 2024-09-20 | Passed
|  | LOG-IN-004 | B1. User input incorrect email or password | Hệ thống thông báo Email or Password invalid | Abnormal | Nguyen Huu Hieu | System display: Email or Password invalid | HieuNH | 2024-09-20 | Passed
|  | LOG-IN-005 | B1. user input email not exist in system | Hệ thống thông báo Email does not exist | Abnormal | Nguyen Huu Hieu | System display: Email does not exist | HieuNH | 2024-09-20 | Passed
|  |  |  | Type | Num of TC
|  |  |  | Small | 5
|  |  |  | Medium | 0
|  |  |  | Complex | 5

## ChangePassword
TEST CASES FOR CHANGE PASSWORD SCREEN
CREATE TEST CASE | [6 empty] | Excution |  |  |  | Fixing Bug |  |  |  | Confirmation Check
Functional Requirement (URD) | Sub Requirement | Test Case ID | Test case Description | Expected output | Type | Create By | Actual Output | Tester | Date | Result | PIC | Root course | Solution | Fixed Date | Tester | Confirm Date | Final Confirm
Allows the user to enter Old password & New password & Confirm password to change password | R1.Allows the user to enter Old password & New password & Confirm password to change password | CHANGE-PASSWORD-001 | Test screen có đủ thông tin không | Màn hình có đầy đủ thông tin như yêu cầu: Old password & New password & Confirm password | Screen layout | Le Viet Hoang |  | HoangLV | 2024-09-20 | Passed
| R2. After user click Change Password button, the Online Shop system will show message | CHANGE-PASSWORD-002 | B1: User nhập sai Old Password B2: Nhấn Change Password | Hệ thống báo "Old password is incorrect" | Abnormal | Le Viet Hoang | Hệ thống báo "Old password is incorrect" | HoangLV | 2024-09-20 | Passed
|  | CHANGE-PASSWORD-003 | B1: User nhập New password không đúng điều kiện | Hệ thống thông báo "Password must has at least 8 characters, 1 uppercase letter, 1 special letter" | Abnormal | Le Viet Hoang | Hệ thống thông báo "Password must has at least 8 characters, 1 uppercase letter, 1 special letter" | HoangLV | 2024-09-20 | Passed
|  | CHANGE-PASSWORD-004 | B1. User nhập Confirm password không khớp với New password | Hệ thống thông báo "Confirm password does not match with New password" | Abnormal | Le Viet Hoang | Hệ thống thông báo "Confirm password does not match with New password" | HoangLV | 2024-09-20 | Passed
|  |  |  | Type | Num of TC
|  |  |  | Small | 4
|  |  |  | Medium | 0
|  |  |  | Complex | 4

## ProductList-Marketer
TEST CASES FOR PRODUCT LIST SCREEN
CREATE TEST CASE | [6 empty] | Excution |  |  |  | Fixing Bug |  |  |  | Confirmation Check
Functional Requirement (URD) | Sub Requirement | Test Case ID | Test case Description | Expected output | Type | Create By | Actual Output | Tester | Date | Result | PIC | Root course | Solution | Fixed Date | Tester | Confirm Date | Final Confirm
Show the paginated list of products, filter the product by category, status or search by title, brief info, sortable by title, category, list price, sale price, featured, or status | R1.Allows the user to view list product | PL-001 | Test screen có đủ thông tin không | Màn hình có đầy đủ thông tin như yêu cầu: products' id, thumbnail, title, category, list price, sale price, featured, and status information | Screen layout | HieuNH |  | HieuNH | 2024-10-04 | Passed
| R2.Allows the user to filter product | PL-002 | B1: User nhập tên sản phẩm không có trong database B2: Nhấn filter | Hệ thống báo "No products available." | Abnormal | HieuNH | Hệ thống báo "No products available." | HieuNH | 2024-10-04 | Passed
|  | PL-003 | B1: User chọn sản phẩm phân loại không có trong database B2: Nhấn filter | Hệ thống báo "No products available." | Abnormal | HieuNH | Hệ thống báo "No products available." | HieuNH | 2024-10-04 | Passed
|  | PL-004 | B1: User chọn sản phẩm trạng thái không có trong database B2: Nhấn filter | Hệ thống báo "No products available." | Abnormal | HieuNH | Hệ thống báo "No products available." | HieuNH | 2024-10-04 | Passed
|  |  |  | Type | Num of TC
|  |  |  | Small | 4
|  |  |  | Medium | 0
|  |  |  | Complex | 4

## ProductDetail-Marketer
TEST CASES FOR PRODUCT DETAIL SCREEN
CREATE TEST CASE | [6 empty] | Excution |  |  |  | Fixing Bug |  |  |  | Confirmation Check
Functional Requirement (URD) | Sub Requirement | Test Case ID | Test case Description | Expected output | Type | Create By | Actual Output | Tester | Date | Result | PIC | Root course | Solution | Fixed Date | Tester | Confirm Date | Final Confirm
Show detailed product information (thumbnail, category, title, brief information, attached images, description, quantity, list price, sale price, flag to turn the featurning on/off, status), from that allow the user to input, view or edit them | R1.Allows the user to view a product | PL-001 | Test screen có đủ thông tin không | Màn hình có đầy đủ thông tin như yêu cầu: products' id, thumbnail, title, category, list price, sale price, featured, and status information | Screen layout | HieuNH |  | HieuNH | 2024-10-05 | Passed
| R2.After user click Update button, the Online Shop system will show message | PL-002 | B1: User giá bán cao hơn giá gốc B2: Nhấn update | Hệ thống báo "Sale price cannot be greater than the original price." | Abnormal | HieuNH | Hệ thống báo "Sale price cannot be greater than the original price." | HieuNH | 2024-10-05 | Passed
|  | PL-003 | B1: User tên sản phẩm có chứa space ( a) B2: Nhấn update | Hệ thống báo "Product name cannot start or end with spaces.." | Abnormal | HieuNH | Hệ thống báo "Product name cannot start or end with spaces.." | HieuNH | 2024-10-05 | Passed
|  | PL-004 | B1: User màu sản phẩm có chứa space ( a) B2: Nhấn update | Hệ thống báo "Color or Sizes must be provided and cannot contain only spaces.." | Abnormal | HieuNH | Hệ thống báo "Color or Sizes must be provided and cannot contain only spaces.." | HieuNH | 2024-10-05 | Passed
|  |  |  | Type | Num of TC
|  |  |  | Small | 4
|  |  |  | Medium | 0
|  |  |  | Complex | 4

## AddProduct-Marketer
TEST CASES FOR ADD PRODUCT SCREEN
CREATE TEST CASE | [6 empty] | Excution |  |  |  | Fixing Bug |  |  |  | Confirmation Check
Functional Requirement (URD) | Sub Requirement | Test Case ID | Test case Description | Expected output | Type | Create By | Actual Output | Tester | Date | Result | PIC | Root course | Solution | Fixed Date | Tester | Confirm Date | Final Confirm
Add new product information (thumbnail, category, title, brief information, attached images, description, quantity, list price, sale price, flag to turn the featurning on/off, status), from that allow the user to input, add them | R1.Allows the user to add a product | PL-001 | Test screen có đủ thông tin không | Màn hình có đầy đủ thông tin như yêu cầu: products' id, thumbnail, title, category, list price, sale price, featured, and status information để thêm mới sản phẩm | Screen layout | HieuNH |  | HieuNH | 2024-10-05 | Passed
| R2.After user click Create button, the Online Shop system will show message | PL-002 | B1: User giá bán cao hơn giá gốc B2: Nhấn update | Hệ thống báo "Sale price cannot be greater than the original price." | Abnormal | HieuNH | Hệ thống báo "Sale price cannot be greater than the original price." | HieuNH | 2024-10-05 | Passed
|  | PL-003 | B1: User tên sản phẩm có chứa space ( a) B2: Nhấn update | Hệ thống báo "Product name cannot start or end with spaces.." | Abnormal | HieuNH | Hệ thống báo "Product name cannot start or end with spaces.." | HieuNH | 2024-10-05 | Passed
|  | PL-004 | B1: User màu sản phẩm có chứa space (a ) B2: Nhấn update | Hệ thống báo "Color or Sizes must be provided and cannot contain only spaces.." | Abnormal | HieuNH | Hệ thống báo "Color or Sizes must be provided and cannot contain only spaces.." | HieuNH | 2024-10-05 | Passed
|  |  |  | Type | Num of TC
|  |  |  | Small | 4
|  |  |  | Medium | 0
|  |  |  | Complex | 4

## Payment
TEST CASES FOR PAYMENT SCREEN
CREATE TEST CASE | [6 empty] | Excution |  |  |  | Fixing Bug |  |  |  | Confirmation Check
Functional Requirement (URD) | Sub Requirement | Test Case ID | Test case Description | Expected output | Type | Create By | Actual Output | Tester | Date | Result | PIC | Root course | Solution | Fixed Date | Tester | Confirm Date | Final Confirm
Payment via VNPay, Credit Card | R1.Allows the user to payment order | PL-001 | Test screen có đủ thông tin không | Màn hình có đầy đủ thông tin như yêu cầu: số tiền, thời gian, nội dung | Screen layout | HieuNH |  | HieuNH | 2024-10-05 | Passed
| R2.After user click Pay button, the Online Shop system will redirect cart completion screen if success | PL-002 | B1: User thanh toán qua credit card B2: Nhấn pay | Hệ thống chuyển tới trang cart completion | Abnormal | HieuNH | Hệ thống chuyển tới trang cart completion | HieuNH | 2024-10-05 | Passed
|  |  |  | Type | Num of TC
|  |  |  | Small | 2
|  |  |  | Medium | 0
|  |  |  | Complex | 2

## ForgotPassword
TEST CASES FOR Forgot PASSWORD SCREEN
CREATE TEST CASE | [6 empty] | Excution |  |  |  | Fixing Bug |  |  |  | Confirmation Check
Functional Requirement (URD) | Sub Requirement | Test Case ID | Test case Description | Expected output | Type | Create By | Actual Output | Tester | Date | Result | PIC | Root course | Solution | Fixed Date | Tester | Confirm Date | Final Confirm
Allows the user to enter Email, New Password, Confirm Password and Reset button | R1.Allows the user to enter Email to get OTP code | FORGOT-PASSWORD-001 | Test screen có đủ thông tin không | Màn hình có đầy đủ thông tin như yêu cầu: New password & Confirm password | Screen layout | Le Viet Hoang |  | HoangLV | 2024-09-20 | Passed
| R2. After that user will be redirected to input New password | FORGOT-PASSWORD-002 | B1: User nhập sai mã OTP được gửi về | Hệ thống báo "Your OTP code is wrong" | Abnormal | Le Viet Hoang | Hệ thống báo "Your OTP code is wrong" | HoangLV | 2024-09-20 | Passed
|  | FORGOT-PASSWORD-003 | B1: User nhập New password không đúng điều kiện | Hệ thống thông báo "Password must has at least 8 characters, 1 uppercase letter, 1 special letter" | Abnormal | Le Viet Hoang | Hệ thống thông báo "Password must has at least 8 characters, 1 uppercase letter, 1 special letter" | HoangLV | 2024-09-20 | Passed
|  | FORGOT-PASSWORD-004 | B1. User nhập Confirm password không khớp với New password | Hệ thống thông báo "Confirm password does not match with New password" | Abnormal | Le Viet Hoang | Hệ thống thông báo "Confirm password does not match with New password" | HoangLV | 2024-09-20 | Passed
|  |  |  | Type | Num of TC
|  |  |  | Small | 4
|  |  |  | Medium | 0
|  |  |  | Complex | 4

## Logout
TEST CASES FOR LOGOUT
CREATE TEST CASE | [6 empty] | Excution |  |  |  | Fixing Bug |  |  |  | Confirmation Check
Functional Requirement (URD) | Sub Requirement | Test Case ID | Test case Description | Expected output | Type | Create By | Actual Output | Tester | Date | Result | PIC | Root course | Solution | Fixed Date | Tester | Confirm Date | Final Confirm
This use case allows users can logout the system | R1. Allows the user click to logout button can logout the system | LOG-OUT-001 | Test screen có đủ thông tin không | Màn hình có đầy đủ thông tin như yêu cầu: email, password, Login button, Forgot password | Screen layout | Nguyen Huu Hieu |  | HieuNH | 2024-09-20 | Passed
| R2. After user click logout button, account user will logout system | LOG-OUT-002 | B1: User click to logout button at header | - User được loggout khỏi hệ thống | Abnormal | Nguyen Huu Hieu |  | HieuNH | 2024-09-20 | Passed
|  |  |  | Type | Num of TC
|  |  |  | Small | 2
|  |  |  | Medium | 0
|  |  |  | Complex | 2

## Home Page
TEST CASES FOR HOME PAGE SCREEN
CREATE TEST CASE | [6 empty] | Excution |  |  |  | Fixing Bug |  |  |  | Confirmation Check
Functional Requirement (URD) | Sub Requirement | Test Case ID | Test case Description | Expected output | Type | Create By | Actual Output | Tester | Date | Result | PIC | Root course | Solution | Fixed Date | Tester | Confirm Date | Final Confirm
Show sliders, hot posts, featured products + the sider with the latest posts, static contacts/links - Shown slider information includes its image and title; the user is redirected to the slider's backlink on his/her clicking - Shown post information includes its thumbnail, title, brief-info; the user is redirected to the post's details on his/her clicking - Shown product information includes its thumbnail, title, brief information; the user is redirected to the product's details on his/her clicking | R1. Show sliders, hot posts, featured products + the sider with the latest posts, static contacts/links | HOME-001 | Test screen có đủ thông tin không | Màn hình có đầy đủ thông tin như yêu cầu: slider, posts, products, link to post detail and product detail | Screen layout | Nguyen Huu Hieu |  | HieuNH | 2024-09-20 | Passed
| R2. Shown post information includes its thumbnail, title, brief-info; the user is redirected to the post's details on his/her clicking | HOME-002 | B1: Truy cập home page bằng url /home B2: Click post B3: User redirect to post detail | - User được đưa đến post detail | Abnormal | Nguyen Huu Hieu |  | HieuNH
| R3. Shown product information includes its thumbnail, title, brief information; the user is redirected to the product's details on his/her clicking | HOME-003 | B1: Truy cập home page bằng url /home B2: Click product B3: User redirect to product detail | - User được đưa đến product detail | Abnormal | Nguyen Huu Hieu |  | HieuNH
| R4. Shown slider information includes its image and title; the user is redirected to the slider's backlink on his/her clicking | HOME-004 | B1: Truy cập home page bằng url /home B2: Click to slider B3: User is redirect to the slider backlink | - User được đưa đến trang qua backlink | Abnormal | Nguyen Huu Hieu |  | HieuNH | 2024-09-20 | Passed
|  |  |  | Type | Num of TC
|  |  |  | Small | 4
|  |  |  | Medium | 0
|  |  |  | Complex | 4

## Remember Account
TEST CASES FOR REMEMBER ACCOUNT
CREATE TEST CASE | [6 empty] | Excution |  |  |  | Fixing Bug |  |  |  | Confirmation Check
Functional Requirement (URD) | Sub Requirement | Test Case ID | Test case Description | Expected output | Type | Create By | Actual Output | Tester | Date | Result | PIC | Root course | Solution | Fixed Date | Tester | Confirm Date | Final Confirm
Remember email and password | R1. Allows the user to click/unclick to checkbox Remember Me | RM-001 | Test screen có đủ thông tin không | Có đầy đủ thông tin như yêu cầu: checkbox Remember Me | Screen layout | Nguyen Huu Hieu |  | HieuNH | 2024-09-20 | Passed
| R2. After user click/unclick Remember Me checkbox, the Online Shop system will save email and password this user | RM-002 | B1: Gọi màn hình Login từ Home Page hoặc url /login B2: Ấn vào check box Remember Me | - Email và Password của người dùng được lưu lại cho phiên đăng nhập tiếp theo | Abnormal | Nguyen Huu Hieu |  | HieuNH | 2024-09-20 | Passed
|  | RM-003 | B1: Gọi màn hình Login từ Home Page hoặc url /login B2: Không ấn vào check box Remember Me | - Không lưu Email và Password của người dùng | Abnormal | Nguyen Huu Hieu |  | HieuNH | 2024-09-20 | Passed
|  |  |  | Type | Num of TC
|  |  |  | Small | 3
|  |  |  | Medium | 0
|  |  |  | Complex | 3

## Register
TEST CASES FOR SIGN UP SCREEN
CREATE TEST CASE | [6 empty] | Excution |  |  |  | Fixing Bug |  |  |  | Confirmation Check
Functional Requirement (URD) | Sub Requirement | Test Case ID | Test case Description | Expected output | Type | Create By | Actual Output | Tester | Date | Result | PIC | Root course | Solution | Fixed Date | Tester | Confirm Date | Final Confirm
Allows the user to register himself/herself to the system by inputing following information: full name, gender, email, mobile, and address; User then need to verify by clicking the link sent via email to him/her before being able to access the system | R1. Allow guest to input email, password, fullname, phone number, sex(male/female), address and Sign up button. | REGISTER-001 | Test screen có đủ thông tin không | Màn hình có đầy đủ thông tin như yêu cầu: email, password, fullname, phone number, sex(male/female), address and Register button. | Screen layout | Nguyen Khang Linh |  | LinhNK |  | Passed
| R2. After user click Sign up button, the system will send an email to require the user to confirm the info of account. | REGISTER-002 | B1: Gọi màn hình Register từ Login screen B2: Nhập thông tin user với email mới và click Register button B3: Mở email kiểm tra confirm email B4: Click vào link để Activate accounnt B5: Chuyển về màn hình home | - User được đưa đến màn hình home ở trạng thái đã login - Thông tin được lưu đúng, đủ trong DB | Abnormal | Nguyen Khang Linh |  | LinhNK |  | Passed
|  | REGISTER-003 | B1: Nhập thông tin user với 1 email đã tồn tại rồi click Sign up button | Hệ thống thông báo email đã tồn tại | Abnormal | Nguyen Khang Linh |  | LinhNK |  | Passed
|  | REGISTER-004 | B1. Nhập password sai business rule (ít nhất 8 ký tự, bắt đầu bằng chữ cái viết hoa, có ít nhất 1 ký tự đặc biệt) | Hệ thống thông báo password không hợp lệ | Abnormal | Nguyen Khang Linh |  | LinhNK |  | Passed
|  |  |  | Type | Num of TC
|  |  |  | Small | 5
|  |  |  | Medium | 0
|  |  |  | Complex | 0

## Product Details
TEST CASES FOR SIGN UP SCREEN
CREATE TEST CASE | [6 empty] | Excution |  |  |  | Fixing Bug |  |  |  | Confirmation Check
Functional Requirement (URD) | Sub Requirement | Test Case ID | Test case Description | Expected output | Type | Create By | Actual Output | Tester | Date | Result | PIC | Root course | Solution | Fixed Date | Tester | Confirm Date | Final Confirm
Show product details (including title, category, images, original price, sale price, and product details) + the sider with the product search box, product categories, the latest products, and static contacts/links | R1. Show product details (including title, category, images, original price, sale price, and product details) | PD-001 | Test screen có đủ thông tin không | Màn hình có đầy đủ thông tin như yêu cầu: name, image, color, size, add to cart | Screen layout | Nguyen Khang Linh |  | LinhNK |  | Passed
| R2. Customer can buy the product by add the product to a cart | PD-002 | B1: Nhấn vào product B2: Thông tin product được đẩy lên màn hình B3: Có thể chọn size và color | - User được đưa đến màn hình product details - Thông tin được đẩy lên từ DB | Abnormal | Nguyen Khang Linh |  | LinhNK |  | Passed
|  | PD-003 |  |  | Abnormal | Nguyen Khang Linh |  | LinhNK |  | Fail
|  | PD-004 |  |  | Abnormal | Nguyen Khang Linh |  | LinhNK |  | Passed
|  | PD-005 |  |  | Abnormal | Nguyen Khang Linh |  | LinhNK |  | Passed
|  |  |  | Type | Num of TC
|  |  |  | Small | 5
|  |  |  | Medium | 0
|  |  |  | Complex | 0

## Blog LIst
TEST CASES FOR SIGN UP SCREEN
CREATE TEST CASE | [6 empty] | Excution |  |  |  | Fixing Bug |  |  |  | Confirmation Check
Functional Requirement (URD) | Sub Requirement | Test Case ID | Test case Description | Expected output | Type | Create By | Actual Output | Tester | Date | Result | PIC | Root course | Solution | Fixed Date | Tester | Confirm Date | Final Confirm
Show the posts paginatedly (sorted by updated date, paginated) + the sider with the post search box, post categories, the latest posts, and static contacts/links; Shown post information includes its thumbnail, title, brief-info; the user is redirected to the post's details on his/her clicking | F1: Show the posts paginatedly (sorted by updated date, paginated) | Customer-001 | Test screen có đủ thông tin không | Màn hình có đầy đủ thông tin như yêu cầu: title, category, detail, image | Screen layout | Phung Kim Manh |  | ManhPK |  | Passed
| F2: + the sider with the post search box, post categories, the latest posts, and static contacts/links; F3: Shown post information includes its thumbnail, title, brief-info; the user is redirected to the post's details on his/her clicking | Customer-002 | Gọi màn hình bloglist từ Login screen | - User được đưa đến màn hình bloglist - Thông tin được hiện đúng, đủ trong DB | Abnormal | Phung Kim Manh |  | ManhPK |  | Passed
|  | Customer-003 | chọn category và filter | hiện list các blog theo category được chọn | Abnormal | Phung Kim Manh |  | manhPK |  | Passed
|  | Customer-004 | back lại blog list | trở lại trang blog list | Abnormal | Phung Kim Manh |  | ManhPK |  | Passed
|  |  |  | Type | Num of TC
|  |  |  | Small | 5
|  |  |  | Medium | 0
|  |  |  | Complex | 0

## Blog Detail
TEST CASES FOR SIGN UP SCREEN
TEST CASES FOR SIGN UP SCREEN
| CREATE TEST CASE | [6 empty] | Excution |  |  |  | Fixing Bug |  |  |  | Confirmation Check
| Functional Requirement (URD) | Sub Requirement | Test Case ID | Test case Description | Expected output | Type | Create By | Actual Output | Tester | Date | Result | PIC | Root course | Solution | Fixed Date | Tester | Confirm Date | Final Confirm
| Show post details (including title, author, updated date, category, and post details) + the sider with the post search box, post categories, static contacts/links | F1: Show post details (including title, author, updated date, category, and post details) | Customer-001 | Test screen có đủ thông tin không | Màn hình có đầy đủ thông tin như yêu cầu: title, category, detail, image | Screen layout | Phung Kim Manh |  | ManhPK |  | Passed
|  | F2: + the sider with the post search box, post categories, static contacts/links | Customer-002 | có các nút tìm kiếm và phân loại | khi chọn sẽ được lọc những bài viết theo yêu cầu | Abnormal | Phung Kim Manh |  | ManhPK |  | Not Passed
[5 empty] | Type | Num of TC
[5 empty] | Small | 2
[5 empty] | Medium | 0
[5 empty] | Complex | 0

## UserProfile
TEST CASES FOR SIGN UP SCREEN
TEST CASES FOR SIGN UP SCREEN
| CREATE TEST CASE | [6 empty] | Excution |  |  |  | Fixing Bug |  |  |  | Confirmation Check
| Functional Requirement (URD) | Sub Requirement | Test Case ID | Test case Description | Expected output | Type | Create By | Actual Output | Tester | Date | Result | PIC | Root course | Solution | Fixed Date | Tester | Confirm Date | Final Confirm
| This is a pop-up screen which allows the user to edit his/her profile information, including the registered ones & the avatar image. Please note that s/he is not allowed to change the email | F1: 'This is a pop-up screen which allows the user to edit his/her profile information, including the registered ones & the avatar image. | Customer-001 | Test screen có đủ thông tin và chỗ để chỉnh sửa không | Màn hình có đầy đủ thông tin như yêu cầu. Sau khi thay đổi thông tin thông tin mới sẽ hiện | Screen layout | Phung Kim Manh |  | ManhPK |  | Passed
|  | F2: Please note that s/he is not allowed to change the email | Customer-002 | không cho chỉnh sửa email | không cho chỉnh sửa email | Abnormal | Phung Kim Manh |  | ManhPK |  | Passed
[5 empty] | Type | Num of TC
[5 empty] | Small | 2
[5 empty] | Medium | 0
[5 empty] | Complex | 0

## OrderList(Seller)
TEST CASES FOR ORDER LIST SCREEN
TEST CASES FOR ORDER LIST SCREEN
| CREATE TEST CASE | [6 empty] | Excution |  |  |  | Fixing Bug |  |  |  | Confirmation Check
| Functional Requirement (URD) | Sub Requirement | Test Case ID | Test case Description | Expected output | Type | Create By | Actual Output | Tester | Date | Result | PIC | Root course | Solution | Fixed Date | Tester | Confirm Date | Final Confirm
| Show the list of orders paginatedly - The list can be shorted by the order date, customer name, total cost, status - Each order include below information: id, ordered date, customer name, product (first product name & number of other products if any), total cost, status; - Allow the users to filter the order by the order date (from, to), sale name, status - Allow the user to search the orders by order id, customer name - On clicking the link under the order id, user would be redirected to the Order Details page | F1: Show the list of orders paginatedly | OrderList-001 | Test screen có show theo page hay không và đủ thông tin theo yêu cầu hay không | Test screen có show theo page và đủ thông tin theo yêu cầu | Screen layout | DungNV | Test screen có show theo page và đủ thông tin theo yêu cầu | DungNV | 2024-10-19 | Passed
|  | F2: - The list can be shorted by the order date, customer name, total cost, status | OrderList-002 | Data có thể sort theo các cột order date, customer name, total cost, status hay không | Data có thể sort theo các cột order date, customer name, total cost, status | Screen function | DungNV | Data có thể sort theo các cột order date, customer name, total cost, status | DungNV | 2024-10-19 | Passed
|  | F3: - Each order include below information: id, ordered date, customer name, product (first product name & number of other products if any), total cost, status; | OrderList-003 | Các thông tin show ra ở bảng có đủ các trường cần thiết hay không | Các thông tin show ra ở bảng có đủ các trường cần thiết | Screen function | DungNV | Các thông tin show ra ở bảng có đủ các trường cần thiết | DungNV | 2024-10-19 | Passed
|  | F4: - Allow the users to filter the order by the order date (from, to), sale name, status | OrderList-004 | Có thể tìm kiếm đc thông tin theo order date (from, to), sale name, status | Có thể tìm kiếm đc thông tin theo order date (from, to), sale name, status | Screen function | DungNV | Có thể tìm kiếm đc thông tin theo order date (from, to), sale name, status | DungNV | 2024-10-19 | Passed
|  | F5: - Allow the user to search the orders by order id, customer name | OrderList-005 | Có thể tìm kiếm đc thông tin theo order id, customer name | Có thể tìm kiếm đc thông tin theo order id, customer name | Screen function | DungNV | Có thể tìm kiếm đc thông tin theo order id, customer name | DungNV | 2024-10-19 | Passed
|  | F6: - On clicking the link under the order id, user would be redirected to the Order Details page | OrderList-006 | Có thể chuyển đến màn order detail đc hay không | Có thể chuyển đến màn order detail | Screen function | DungNV | Có thể chuyển đến màn order detail | DungNV | 2024-10-19 | Passed
[5 empty] | Type | Num of TC
[5 empty] | Small | 0
[5 empty] | Medium | 6
[5 empty] | Complex | 0

## OrderDetail(Seller)
TEST CASES FOR ORDER DETAIL SCREEN
TEST CASES FOR ORDER DETAIL SCREEN
| CREATE TEST CASE | [6 empty] | Excution |  |  |  | Fixing Bug |  |  |  | Confirmation Check
| Functional Requirement (URD) | Sub Requirement | Test Case ID | Test case Description | Expected output | Type | Create By | Actual Output | Tester | Date | Result | PIC | Root course | Solution | Fixed Date | Tester | Confirm Date | Final Confirm
| Show the order details, including the following information: - Basic order information: order id, customer full name, email, mobile, order date, total cost, sale name, status - The receiver information: full name, gendar, email, mobile, address - This list of ordered products, each product include following information: thumbnail, name, category, unit price, quantity, total cost Sale Manager & the assigned Sale can change the order status & the sale notes Sale Manager can assign the order to other sale | F1: - Basic order information: order id, customer full name, email, mobile, order date, total cost, sale name, status | OrderDetail-001 | Test screen có show đủ thông tin theo yêu cầu hay không | Test screen có show đủ thông tin theo yêu cầu | Screen layout | DungNV | Test screen có show đủ thông tin theo yêu cầu | DungNV | 2024-10-19 | Passed
|  | F2: - The receiver information: full name, gendar, email, mobile, address | OrderDetail-002 | Test screen có show đủ thông tin theo yêu cầu hay không | Test screen có show đủ thông tin theo yêu cầu | Screen layout | DungNV | Test screen có show đủ thông tin theo yêu cầu | DungNV | 2024-10-19 | Passed
|  | F3: - This list of ordered products, each product include following information: thumbnail, name, category, unit price, quantity, total cost | OrderDetail-003 | Test screen có show đủ thông tin theo yêu cầu hay không | Test screen có show đủ thông tin theo yêu cầu | Screen layout | DungNV | Test screen có show đủ thông tin theo yêu cầu | DungNV | 2024-10-19 | Passed
|  | F4: Sale Manager & the assigned Sale can change the order status & the sale notes | OrderDetail-004 | Có thể update đc order status được hay không | Có thể update đc order status được | Screen function | DungNV | Có thể update đc order status được | DungNV | 2024-10-19 | Passed
|  | F5: Sale Manager can assign the order to other sale | OrderDetail-005 | Có thể update đc thông tin sale phụ trách order được hay không | Có thể update đc thông tin sale phụ trách order | Screen function | DungNV | Có thể update đc thông tin sale phụ trách order | DungNV | 2024-10-19 | Passed
[5 empty] | Type | Num of TC
[5 empty] | Small | 0
[5 empty] | Medium | 5
[5 empty] | Complex | 0

## SaleDashBoard
TEST CASES FOR SALE DASHBOARD SCREEN
TEST CASES FOR SALE DASHBOARD SCREEN
| CREATE TEST CASE | [6 empty] | Excution |  |  |  | Fixing Bug |  |  |  | Confirmation Check
| Functional Requirement (URD) | Sub Requirement | Test Case ID | Test case Description | Expected output | Type | Create By | Actual Output | Tester | Date | Result | PIC | Root course | Solution | Fixed Date | Tester | Confirm Date | Final Confirm
| Show the trend of success/total orders, and the revenues trends by day for the last 7 days for all or a specific sale person (the start date, end date, sale, order status can be adjustable) | F1: 'Show the trend of success/total orders, | SaleDashboard-001 | Test screen có show được chart cho số lượng order hay không | Test screen có show đủ thông tin theo yêu cầu | Screen layout | DungNV | Test screen có show đủ thông tin theo yêu cầu | DungNV | 2024-10-19 | Passed
|  | F2: and the revenues trends | SaleDashboard-002 | Test screen có show được chart cho revenue hay không | Test screen có show được chart cho revenue | Screen layout | DungNV | Test screen có show được chart cho revenue | DungNV | 2024-10-19 | Passed
|  | F3: by day for the last 7 days for all or a specific sale person (the start date, end date, sale, order status can be adjustable) | SaleDashboard-003 | Có thể filter chart theo start date, end date, sale, order status hay không | Có thể filter chart theo start date, end date, sale, order status | Screen function | DungNV | Có thể filter chart theo start date, end date, sale, order status | DungNV | 2024-10-19 | Passed
[5 empty] | Type | Num of TC
[5 empty] | Small | 0
[5 empty] | Medium | 3
[5 empty] | Complex | 0

## Setting list
TEST CASES FOR SETTING LIST SCREEN
TEST CASES FOR SALE SETTING LIST
| CREATE TEST CASE | [6 empty] | Excution |  |  |  | Fixing Bug |  |  |  | Confirmation Check
| Functional Requirement (URD) | Sub Requirement | Test Case ID | Test case Description | Expected output | Type | Create By | Actual Output | Tester | Date | Result | PIC | Root course | Solution | Fixed Date | Tester | Confirm Date | Final Confirm
| Show the paginated list of settings (include settings' id, type, value, order, status): - The admin can filter the setting by type, status - Allow the admin to seach settings by value - From each setting, the admin can choose to view, activate/deactivate, or edit it - The page also have the button/link that allows the admin to add new setting | F1: The admin can filter the setting by type, status | Setting list-001 | Có thể filter theo type, status hay không | Có thể filter theo type, status | Screen function | DungNV | Có thể filter theo type, status | DungNV | 2024-10-30 | Passed
|  | F2: Allow the admin to seach settings by value | Setting list-002 | Có thể search theo value hay không | Có thể search theo value | Screen function | DungNV | Có thể search theo value | DungNV | 2024-10-30 | Passed
|  | F3: From each setting, the admin can choose to view, activate/deactivate, or edit it | Setting list-003 | có thể chuyển sang trang edit, view được hay không | có thể chuyển sang trang edit, view | Screen function | DungNV | có thể chuyển sang trang edit, view | DungNV | 2024-10-30 | Passed
|  | F4: The page also have the button/link that allows the admin to add new setting | Setting list-004 | có thể chuyển sang trang add new được hay không | có thể chuyển sang trang add new | Screen function | DungNV | có thể chuyển sang trang add new | DungNV | 2024-10-30 | Passed
[5 empty] | Type | Num of TC
[5 empty] | Small | 4
[5 empty] | Medium | 0
[5 empty] | Complex | 0

## Setting detail
TEST CASES FOR SETTING DETAIL SCREEN
TEST CASES FOR SALE SETTING DETAIL
| CREATE TEST CASE | [6 empty] | Excution |  |  |  | Fixing Bug |  |  |  | Confirmation Check
| Functional Requirement (URD) | Sub Requirement | Test Case ID | Test case Description | Expected output | Type | Create By | Actual Output | Tester | Date | Result | PIC | Root course | Solution | Fixed Date | Tester | Confirm Date | Final Confirm
| Show detailed user information (type, value, order, description, status), from that allow the user to add new, view or edit setting information | F1: detailed user information (type, value, order, description, status) | Setting detail-001 | Có show ra đủ thông tin theo yêu cầu hay không | Có show ra đủ thông tin theo yêu cầu | Screen layout | DungNV | Có show ra đủ thông tin theo yêu cầu | DungNV | 2024-10-30 | Passed
|  | F2: from that allow the user to add new | Setting detail-002 | Có thể add new đc category hay không | Có thể add new đc category | Screen function | DungNV | Có thể add new đc category | DungNV | 2024-10-30 | Passed
|  | F3: view or edit setting information | Setting detail-003 | Có thể edit, view đc category có sẵn hay không | Có thể edit, view đc category có sẵn hay | Screen function | DungNV | Có thể edit, view đc category có sẵn hay | DungNV | 2024-10-30 | Passed
[5 empty] | Type | Num of TC
[5 empty] | Small | 3
[5 empty] | Medium | 0
[5 empty] | Complex | 0